## Activity Log - Ines
Name: | Ines | Project Group (Name/Number): Software 4 - Group 4
This activity log is for you to document your individual contributions and ideas you have done towards your final group project. This will be submitted to your instructors along with your project code. You can document how many minutes you spent working on your code, when you had team meetings outside of the class sessions, or use this as a way to take notes for your own viewing. This is to be completed individually.
Week: | Date: | Activity/Task: | Time spent on Activity: | Team Members Involved | Completed? | Notes:
1 | 2023-11-15 | Added some group name ideas and activities on miro | 15 minutes | 1 | Yes
1 | 2023-11-17 | Group meeting | 1h30 minutes | 6 | Yes
2 | 2023-11-20 | Created the activity log excel file and added the main tasks completed by the team members; updated jira and google drive | 1h | 1 | Yes | The activity file will be completed along with the project
2 | 2023-11-20 | Created pdf file of our project, started introduction, updated jira and google drive | 30 minutes | 1 | Yes
2 | 2023-11-21 | Group meeting at lunch time and at night | 2h | 6 | Yes
2 | 2023-11-22 | Created suggestions for queries and routes for group project | 20 minutes | 1 | Yes
2 | 2023-11-23 | Updating homework 2 | 20 minutes | 1 | Yes | The homework will keep being updated
2 | 2023-11-24 | Group meeting | 1h | 6 | Yes
2 | 2023-11-25 | Creating API endpoint for getting activity by ID, modifying files and creating function to get all activities | 3h | 1 | Yes
2 | 2023-11-26 | Group meeting and figuring structure for APIs | 3h | 5 | Yes
3 | 2023-11-27 | Searching solution for TypeError on timedelta and sharing it with the group | 1h | 1 | Yes
3 | 2023-11-28 | Team meeting to review homework 2 | 45 minutes | 4 | Yes
3 | 2023-11-28 | Reviewing homework 2 formating and deliver homework 2 | 15 minutes | 1 | Yes
3 | 2023-12-02 | Creating bootstrap grid and styling | 2h | 1 | Yes
3 | 2023-12-02 | Reviewing PRs and resolving conflicts, with Sofia | 2h | 2 | Yes
4 | 2023-12-04 | Group meeting to decide and divide next steps to finish back-end | 1h15 minutes | 5 | Yes
4 | 2023-12-09 | Unit tests, updating read me and reviewing a PR | 2h | 1 | Yes
4 | 2023-12-09 | Group meeting | 1h | 5 | Yes
4 | 2023-12-10 | Continue unit tests and review cancel_reservation function | 2h | 1 | Yes
5 | 2023-12-11 | Meeting with Sofia to create weather route | 30 minutes | 2 | Yes
5 | 2023-12-11 | Finishing cancel_reservation UTs and fixing other UT; try to figure cancel reservation route; reviewing and approving PR | 3h | 1 | Yes
5 | 2023-12-12 | Group meeting to decide and divide next steps to finish pdf and code | 45 minutes | 4 | Yes
5 | 2023-12-15 | Write testing on pdf; get back UTs missing on dev; adjust front-end cards heights | 3h | 1 | Yes
5 | 2023-12-16 | Group meeting | 1h | 6 | Yes
5 | 2023-12-16 | Change pdf's formatting and include cover and background | 2h | 1 | Yes
5 | 2023-12-16 | Review pdf's and code | 1h30 | 1 | Yes
5 | 2023-12-17 | Group meeting and delivery of work project | 1h30 | 6 | Yes
Total time:

## Activity Log - Kayla
Name: | Kayla | Project Group (Name/Number): Software 4 - Group 4
This activity log is for you to document your individual contributions and ideas you have done towards your final group project. This will be submitted to your instructors along with your project code. You can document how many minutes you spent working on your code, when you had team meetings outside of the class sessions, or use this as a way to take notes for your own viewing. This is to be completed individually.
Week: | Date: | Activity/Task: | Time spent on Activity: | Team Members Involved | Completed? | Notes:
1 | 2023-11-15 | Added some group name ideas and activities on miro | 15 minutes | 1 | Yes
1 | 2023-11-17 | Group meeting | 1h30 minutes | 6 | Yes
2 | 20-27/11/2023 | HomeWork 2 | 3 hr 30m | 1 | Yes
2 | 2023-11-21 | Group meeting at night | 30 minutes | 6 | Yes
2 | 2023-11-22 | Group meeting at lunch time | 1h | 5 | Yes
2 | 2023-11-22 | Adding queries and route suggestion on miro | 15 mins | 1 | Yes
2 | 2023-11-24 | Group meeting | 1h | 6 | Yes
3 | 2023-11-25 | Creating API endpoint for getting reversation by date, also comparing Inês code to discuss solution for datetime error | 2.5h | 1 | Yes
3 | 2023-11-26 | Group meeting and figuring structure for APIs | 2h | 1 | Yes
3 | 2023-11-26 | Editing codes and files structure related to config.json, config_example.json and .gitignore | 45 mins | 1 | Yes
3 | 2023-11-28 | Group meeting at lunch time | 30 mins | 4 | Yes
3 | 2023-11-28 | API endpoint for updating reservation by id work solo and with Marnie | 1hr15mins | 2 | No
3 | 2023-12-01 | Reviewed pull request | 10mins | 1 | Yes
4 | 2023-12-03 | Reviewed conflict and resubit pull request | 20mins | 1 | Yes
4 | 2023-12-04 | Edit code accordingly with the new mapped format and re-push branch to rsolve conflict | 25 mins | 1 | Yes
4 | 2023-12-04 | working on API for editing reservation date | 30 mins | 1 | No
4 | 2023-12-04 | Group meeting | 30m | 5 | Yes
4 | 2023-12-04 | Meeting with Marnie and Sofia about endpoint for editing reservation date | 1 hr | 3 | Yes
4 | 2023-12-05 | Review Sofia's codes. Resolved conflict on endpoint for editing reservation date subitted PR | 2 hr | 1 | Yes
4 | 2023-12-08 | Repush endpoint for editing reservation date with Vicki's edit Reviewing PRs | 30 mins | 1 | Yes
4 | 2023-12-09 | mmorning meeting with Marnie for report pdf// preparing the report pdf | 2hr40 mins | 2 | No
4 | 2023-12-09 | Afternoon meeting with group | 1hr | 5 | Yes
4 | 2023-12-09 | function for getting equipment id by activity id Added UT for getting reservation by reservation_id and editing reservation date | 3 hr 15 | 1 | Yes
5 | 2023-12-12 | Team meeting | 40minutes | 4 | Yes | planned the work for the next few days
5 | 2023-12-13 | Team meeting | 40minutes | 4 | Yes
5 | 2023-12-15 | report pdf | 1hr30mins | 1 | Yes
5 | 2023-12-16 | Team meeting | 2hr15 mins | 6 | Yes
5 | 2023-12-16 | Cover for pdf | 45 mins | 1 | Yes
5 | 2023-12-17 | Group meeting and delivery of work project | 1h30 | 6 | Yes
Total time:

## Activity Log - Marnie
Name: | Marnie | Project Group (Name/Number): Software 4 - Group 4
This activity log is for you to document your individual contributions and ideas you have done towards your final group project. This will be submitted to your instructors along with your project code. You can document how many minutes you spent working on your code, when you had team meetings outside of the class sessions, or use this as a way to take notes for your own viewing. This is to be completed individually.
Week: | Date: | Activity/Task: | Time spent on Activity: | Team Members Involved | Completed? | Notes:
1 | 2023-11-15 | Added some group name ideas and activities on miro | 15 minutes | 1 | Yes
1 | 2023-11-17 | Group meeting | 1h30 minutes | 6 | Yes
1 | 2023-11-19 | Created the bare bones for homework2 and the bare bones of project presentation. I then updated this info on Jira, and shared the drive link with the team on Jira/Slack | 30 minutes | 1 | Yes | The activity file will be completed along with the project
2 | 2023-11-20 | Added some information to the homework2 q1 | 10 minutes | 1 | Yes
2 | 2023-11-21 | Group meeting at night | 30 minutes | 6 | Yes
2 | 2023-11-21 | Updated the homework 2 document | 40 minutes | 1 | No
2 | 2023-11-24 | Team meeting in the evening | 1h | 6 | Yes
2 | 2023-11-22 | Lunch time meeting (had to leave early due to battery on phone dying) | 15 minutes | 5 | Yes
2 | 2023-11-26 | Sunday evening group meeting | 2h | 5 | Yes
3 | 2023-11-27 | Created routes for cancelling reservation by ID and then creating function to cancel reservation | 1h | 1 | Yes
3 | 2023-11-28 | With Kayla, started working on creating route for updating reservation date and function | 1h | 2 | No
3 | 2023-12-01 | Working on adding to the above route/function | 1h | 1 | No
4 | 2023-12-04 | Group meeting | 30m | 5 | Yes
4 | 2023-12-04 | Editing my API endpoint for deleting a reservation using a new branch | 30m | 1 | Yes
4 | 2023-12-09 | Met with Kayla to start the project document/report | 40m | 2 | No
4 | 2023-12-09 | Team meeting - updates and any issues | 50m | 5 | Yes
4 | 2023-12-10 | Met with Kayla regarding unit testing issues and help with FlaskCors installation | 45m | 2 | Yes
4 | 2023-12-10 | Working on a branch to test get all outdoor/indoor activities | 1h | 1 | No
4 | 2023-12-10 | Working on the project document | 1h | 1 | No
5 | 2023-12-11 | Meeting with Sofia after my unit testing for get all outdoor/indoor activity functions ran into errors | 20m | 2 | Yes
5 | 2023-12-11 | Tidying up my code and using the new code for indoor functions for my outdoor function | 20m | 1 | Yes
5 | 2023-12-12 | Solving branch merges on my unit testing | 20m | 1 | Yes
5 | 2023-12-14 | Completed sections in project document | 1h | 1 | Yes
5 | 2023-12-16 | Meeting with group to run over document, presentation and any other business | 1h 30m | 6 | Yes
5 | 2023-12-17 | Group meeting and delivery of work project | 1h30 | 6 | Yes
Total time:

## Activity Log - Paula
Name: | Paula | Project Group (Name/Number): Software 4 - Group 4
This activity log is for you to document your individual contributions and ideas you have done towards your final group project. This will be submitted to your instructors along with your project code. You can document how many minutes you spent working on your code, when you had team meetings outside of the class sessions, or use this as a way to take notes for your own viewing. This is to be completed individually.
Week: | Date: | Activity/Task: | Time spent on Activity: | Team Members Involved | Completed? | Notes:
1 | 2023-11-12 | Created the group channel on Slack Created the group project repository on Github Prepared the Jira board Announced rules of interacting with Github, intoduced team to Jira Added repository naming convention rules to README.md | 6h | 1 | Yes
1 | 2023-11-15 | Added some group name ideas and activities on miro | 30 minutes | 1 | Yes
1 | 2023-11-17 | Group meeting | 1h30 minutes | 6 | Yes | agreed on the topic, name and next steps
1 | 2023-11-20 | Started to work on homework 2 | 1 h | 1 | Yes
1 | 2023-11-17 | Came up with project file and folder structure and added those to Github | 1h | 1 | Yes
1 | 2023-11-19 | Created project backlog | 2h | 1 | Yes
2 | 2023-11-21 | Create a UML diagram of classes | 4h | 1 | Yes
2 | 2023-11-21 | Group meeting at lunch time and at night | 2h | 6 | Yes
2 | 2023-11-22 | Group meeting at lunch time | 1h | 1 | Yes
2 | 2023-11-22 | Added classes model and config loading | 3h | 1 | Yes
2 | 2023-11-24 | Added the database connection logic | 1h30minutes | 1 | Yes
2 | 2023-11-24 | Group meeting | 1h | 6 | Yes
3 | 2023-11-28 | Add a quickfix for a datetime issues | 1h30minutes | 1 | Yes
3 | 2023-11-28 | Group meeting to finish the homework. | 45minutes | 4 | Yes | Reviewed the homework.
3 | 2023-11-29 | Establish a db connection and create a sample query to mock_db on a frontend side. | 4h | 1 | Yes
4 | 2023-12-08 | Fix the db connection as we have working endpoints. | 2h | 1 | Yes
4 | 2023-12-08 | Create a logo and add a navbar to frontend side. | 2h | 1 | Yes
4 | 2023-12-08 | Start working on reservation form. | 2h30minutes | 1 | No | Work will be continued next day.
4 | 2023-12-09 | Review pull requests and try to address github issues. | 30minutes | 1 | Yes
4 | 2023-12-09 | Team meeting | 1h | 5 | Yes
4 | 2023-12-09 | Continue work on the frontend reservation form. | 7h | 1 | No | Work will be continued next day.
4 | 2023-12-10 | Continue work on the frontend reservation form. | 3h | 1 | Yes | Still needs some adjustments, but waiting for backend.
4 | 2023-12-10 | Adjust backend add_reservation path to work with frontend. | 2h | 1 | Yes
4 | 2023-12-10 | Add a reservation confirmation alert to frontend. | 2h30minutes | 1 | Yes
5 | 2023-12-11 | Add a installation guide to readme.md. | 1h | 1 | Yes
5 | 2023-12-11 | Fix the delete_reservation endpoint. | 2h | 1 | Yes
5 | 2023-12-11 | Review the weather api endpoint | 1h30minutes | 1 | Yes
5 | 2023-12-12 | Add the weather display on the frontend. | 2h | 1 | Yes
5 | 2023-12-12 | Add the 'about us' sub-page. | 2h | 1 | Yes
5 | 2023-12-12 | Team meeting | 40minutes | 4 | Yes | planned the work for the next few days
5 | 2023-12-13 | Pair bug-fixing | 40minutes | 2 | Yes
5 | 2023-12-13 | Writing the project report - functional and non-functional requirements. | 2h30minutes | 1 | Yes
5 | 2023-12-13 | Team meeting to go over last code changes. | 40minutes | 5 | Yes
5 | 2023-12-14 | Fixing bugs in add reservation function in console app | 1h | 1 | Yes
5 | 2023-12-14 | Writing the design and architecture report. | 2h | 1 | No
5 | 2023-12-14 | Refactoring the code and adding comments | 40minutes | 1 | Yes
5 | 2023-12-15 | Writing the design and architecture report. | 1h | 1 | Yes
5 | 2023-12-16 | Team meeting. | 2h15minutes | 6 | Yes
5 | 2023-12-17 | Group meeting and delivery of work project | 1h30 | 6 | Yes
Total time:

## Activity Log - Sofia
Name: | Sofia | Project Group (Name/Number): Software 4 - Group 4
This activity log is for you to document your individual contributions and ideas you have done towards your final group project. This will be submitted to your instructors along with your project code. You can document how many minutes you spent working on your code, when you had team meetings outside of the class sessions, or use this as a way to take notes for your own viewing. This is to be completed individually.
Week: | Date: | Activity/Task: | Time spent on Activity: | Team Members Involved | Completed? | Notes:
1 | 2023-11-15 | Added some group name ideas and activities on miro | 15 minutes | 1 | Yes
1 | 2023-11-17 | Group meeting | 1h30 minutes | 6 | Yes
1 | 2023-11-19 | Added activities' descriptions on miro | 45 minutes | 1 | Yes
2 | 2023-11-21 | Group meeting at lunch time and at night | 2h | 6 | Yes
2 | 2023-11-22 | Reviewed data base creation script | 20 minutes | 1 | Yes
|  | Group meeting at lunch time and at night | 1h | 4 | Yes
2 | 2023-11-23 | Brainstorming ideas for routes and queries | 1h | 1 | Yes
2 | 2023-11-24 | Group meeting | 1h | 6 | Yes
3 | 2023-11-27 | Understanding the weather API chosen and creating function to retrieve data | 2h | 1 | Yes
|  | Reviewed homework 2 (added unit tests part) | 30min | 1 | Yes
3 | 2023-11-28 | Group meeting | 45min | 4 | Yes
3 | 2023-12-02 | Finished function to get weather info for specific date and time (also checks if date and time are valid) | 2h30 | 1 | Yes
|  | API endpoint to insert new reservations | 1h | 1 | Yes
|  | API endpoint to get activity by type (two different endpoints) | 1h | 1 | Yes
|  | Group meeting (Inês) to review pull requests and resolve merge conflicts | 2h | 2 | Yes
|  | Added to Miro board scheme for functions that should be created for checking the weather conditions for each activity | 30min | 1 | Yes
|  | Added step-by-step on how to get API key for weather API | 30min | 1 | Yes
3 | 2023-12-03 | Reviewed pull requests | 20min | 1 | Yes
4 | 2023-12-04 | Group meeting - reviewing all we have done so far and deciding next steps | 1h15min | 5 | Yes
|  | Group meeting (helping Marnie and Kayla with their code) | 1h | 3 | Yes
|  | Creating classes weatherChecker, Activity, Kayaking, testing | 2h30min | 1 | Yes
4 | 2023-12-07 | Reviewed pull requests | 30min | 1 | Yes
4 | 2023-12-09 | Group meeting | 45min | 5 | Yes
5 | 2023-12-11 | Group meeting with Inês (getting API endpoint for the weather) | 30min | 2 | Yes
|  | Finished creating classes on the Weather API and created function that gets the specific message according to the activity and the weather for a specific day and time | 3h | 1 | Yes
|  | Helping Marnie getting Unit Test for indoor activities working | 20min | 2 | Yes
5 | 2023-12-13 | Group meeting | 1h30 | 5 | Yes
|  | Worked on the final pdf | 1h | 5 | Yes
5 | 2023-12-15 | Refactoring code | 1h | 1 | Yes
5 | 2023-12-16 | Fix weather API function in case of invalid date | 30min | 1 | Yes
|  | Group meeting and reviewing code | 2h | 6 | Yes
5 | 2023-12-17 | Group meeting and delivery of work project | 1h30 | 6 | Yes
Total time:

## Activity Log - Vicki
Name: | Vicki | Project Group (Name/Number): Software 4 - Group 4
This activity log is for you to document your individual contributions and ideas you have done towards your final group project. This will be submitted to your instructors along with your project code. You can document how many minutes you spent working on your code, when you had team meetings outside of the class sessions, or use this as a way to take notes for your own viewing. This is to be completed individually.
Week: | Date: | Activity/Task: | Time spent on Activity: | Team Members Involved | Completed? | Notes:
1 | 2023-11-13 | Created the miro board and added structure | 45 minutes | 1 | Yes | Miro board will be changed during the project
1 | 2023-11-15 | Added some group name ideas and activities on miro | 15 minutes | 1 | Yes
1 | 2023-11-17 | Group meeting | 1h30 minutes | 6 | Yes
1 | 2023-11-17 | Created the entity relationship diagram for the database for Thrilltopia | 1h | 1 | Yes | This can be edited until the database is finalised
1 | 2023-11-19 | Added the script for creating the database | 45 minutes | 1 | Yes
1 | 2023-11-19 | Created the equipment for each activity on the miro | 60 minutes | 1 | Yes
2 | 2023-11-21 | Group meeting at lunch time and at night | 2h | 6 | Yes
2 | 2023-11-21 | Changed the SQL script for creating the database and inserted all of the data to populate the database | 4h | 1 | yes | data base is now complete
2 | 2023-11-21 | Added to the group homework document on google drive | 30mins | 1 | Yes | May add more
2 | 2023-11-22 | Team meeting at lunch time and at night time | 1h | 6 | yes
2 | 2023-11-23 | worked on creating functions in db utils and related routes in the main file | 2h |  | yes | ongoing area of work
2 | 2023-11-24 | Team meeting at night | 1h | 6 | yes | discussed where we are up to and what needs to be done
2 | 2023-11-25 | worked on mapping functions for the tables as classes | 3h | 1 | no | ongoing area of work
2 | 2023-11-26 | working on getting sqlAlchemy to work in our application with mapping recreated the application in a different project to try and test and reformat architecture to recreated the application in a different project to try and test and reformat architecture to get the project working without breaking the main application | 4h | 1 | no | ongoing area of work
3 | 2023-11-27 | team call to discuss issues with sqlalchemy and where to go from here, paula explained her logic then I fed back to the team, after clarification a decision was made to revert back to the way we created project 1 as we are more familar and comfortable with this process | 1hr 30 | 6 | yes | decided to revert project to the original format
3 | 2023-11-28 | reviewed group homework | 30mins | 1 | yes
3 | 2023-11-30 | worked on functions in db utils and routes in model file | 2h | 1 | yes | ongoing area of work
3 | 2023-12-02 | continued to work on the functions in db utils and the routes in model, completed them | 4h | 1 | yes
3 | 2023-12-03 | fixed the time delta and duration format issues in all relevant functions and routes | 2h | 1 | yes
4 | 2023-12-04 | team meeting | 1h15mins | 4 | yes
4 | 2023-12-04 | fixed all the functions and routes after testing and started the to create functions in the main file ready for the run function | 4hrs | 1 | yes
4 | 2023-12-06 | reviewed and helped Kayla to fix the edit reservation date api endpoint | 30mins | 2 | yes
4 | 2023-12-06 | fixed the reservation by activity name function | 30mins | 1 | yes
4 | 2023-12-09 | had issues with github and completing review tried to work around but couldn't continued work on the functions in the main file for the run script | 2hr30mins | 1 | yes
4 | 2023-12-10 | finished fixing all errors in the db utils and model and added error handling to the functions | 1hr 30 | 1 | yes
5 | 2023-12-11 | helped Ines with the cancel reservation route along with paula, reviewed the read me file continued working on the main file | 1hr30 | 1 | yes
5 | 2023-12-12 | worked on completing the functions in the main file | 2hrs | 1 | yes
5 | 2023-12-13 | completed work on the backend console application and pushed for review | 2hrs | 1 | yes
5 | 2023-12-13 | team meeting | 1hr | 6 | yes
5 | 2023-12-15 | completed the run function incorporating the requirement for a python library, OrderedDict ran and tested the console application and debugged as much as possible, added comments and error handling where possible | 5hrs | 1 | yes | wooo hooo!
5 | 2023-12-16 | team meeting to discuss final stages of the project and what remains to be done | 1hr30 | 6 | yes | nearly there!
5 | 2023-12-16 | completed checks on the console application with the team, fixed last minute bugs and added final error handling | 30mins | 6 | yes | woop woop we have done it girls!
5 | 2023-12-16 | reviewed, edited and added to the team pdf document | 4hrs | 6 | yes | how do we make it 7 pages!
5 | 2023-12-16 | finally completed my activity log!! | 1hr | 1 | yes | sorry it took so long girls!
5 | 2023-12-17 | Group meeting and delivery of work project | 1h30 | 6 | Yes
Total time: